## Sheet1
Task Name | Outline Level | Duration
Microsoft BizTalk Server | 1 | 464 days
Vision/Scope | 2 | 26.75 days
Evaluate Microsoft BizTalk Server | 3 | 1 wk
Evaluate corporate business objectives | 3 | 1 wk
Determine technology goals and objectives | 3 | 1 wk
Formulate preliminary cost/benefit analysis | 3 | 1 wk
Determine project scope (lab, pilot, international/regional deployment, coexistence strategies, etc) | 3 | 1 wk
Determine major milestones | 3 | 2 days
Secure executive sponsorship/funding | 3 | 1 day
Vision/scope complete | 3 | 0 days
Planning | 2 | 97.25 days
Assemble Project Teams/Define Roles | 3 | 5.5 days
Detail Current Computing Environment | 3 | 10 days
Preliminary Design Objectives | 3 | 12 days
Identify Coexistence Strategies | 3 | 3 days
Establish Test Lab Environment | 3 | 32.75 days
Perform Risk Assessment | 3 | 12 days
Define Communication Strategy | 3 | 13 days
Define Education/Training Strategy | 3 | 9 days
Planning complete | 3 | 0 days
Development | 2 | 220 days
Evaluate Installation Strategies | 3 | 12 days
Active Directory | 3 | 3 days
BizTalk Strategy, Standards, and Management | 3 | 34 days
Security Considerations | 3 | 63 days
Public Key Infrastructure | 3 | 19 days
Remote Desktop Services | 3 | 12 days
High-Availability Applications/Services (Clustering) | 3 | 29 days
Storage Management Strategies | 3 | 26 days
Develop Education/training | 3 | 22 days
Development complete | 3 | 2 days
Proof of Concept (POC) | 2 | 89 days
POC Preparation | 3 | 21 days
Deploy Development Solution to POC Lab Machines | 3 | 76 days
Perform Full-Cycle Risk Assessment | 3 | 13 days
POC complete | 3 | 3 days
Pilot | 2 | 67.5 days
Planning | 3 | 35 days
Deployment | 3 | 8 days
Evaluate the Pilot | 3 | 20 days
Post-Pilot Evaluation | 3 | 4.5 days
Pilot complete | 3 | 0 days
Development | 2 | 62 days
Planning | 3 | 62 days
Development complete | 3 | 0 days
Deployment - Production | 2 | 38.5 days?
Communications | 3 | 2.5 days?
Education/Training | 3 | 5.5 days
Active Directory | 3 | 2.5 days
Security Infrastructure | 3 | 10 days
Public Key Infrastructure | 3 | 8 days
High-Availability Applications/Services (Clustering) | 3 | 7.5 days
Storage Management Strategies | 3 | 12 days
Deployment complete | 3 | 0 days
Post-Implementation Review | 3 | 12 days
Microsoft BizTalk Server Migration Complete | 2